## Sheet1
BloomBudget
Tasks | Responsible | Start Date | Days needed | End Date | Adjusted length
Initiation - Part 1: Research, planning, and design
Introduction | Avuyile, Ondela | 2026-02-17 | 1 | 2026-02-18 | 1
Overview, strengths, and weaknesses,and innovative features | All members | 2026-02-19 | 2 | 2026-02-23 | 4
Infographic features | Olilitha | 2026-02-23 | 1 | 2026-02-24 | 1
List of best features | Tuleka | 2026-02-25 | 2 | 2026-02-27 | 2
Conclusion | Ondela, Avuyile | 2026-02-28 | 1 | 2026-03-02 | 2
Planning and design
Define system requirements | All members | 2026-03-02 | 2 | 2026-03-04 | 2
Implement a questionnaire for personalization | Olilitha | 2026-03-06 | 1 | 2026-03-09 | 3
Create a database schema (User, Categories, Expenses, Budgets, etc.) | Ondela and Avuyile | 2026-03-10 | 3 | 2026-03-13 | 3
Create a prototype mock-ups | All members | 2026-03-16 | 4 | 2026-03-20 | 4
ERD | Tuleka | 2026-03-24 | 1 | 2026-03-25 | 1
Project plan | Avuyile | 2026-03-24 | 2 | 2026-03-26 | 2
Execution
Profile layout | Olilitha | 2026-03-26 | 1 | 2026-03-27 | 1
Settings page | Olilitha | 2026-03-30 | 1 | 2026-04-02 | 3
Develop registration and login feature. | Tuleka, Ondela | 2026-03-31 | 3 | 2026-04-07 | 7
Integrate database schema with app logic. | Ondela | 2026-04-02 | 2 | 2026-04-06 | 4
Develop budget goals feature (monthly + category limits). | Avuyile | 2026-04-06 | 2 | 2026-04-08 | 2
Design an expense entry form | Ondela | 2026-04-08 | 2 | 2026-04-10 | 2
Implement an expense category (create, edit, delete) | Ondela | 2026-04-13 | 2 | 2026-04-15 | 2
Create and design the transactions screen | Tuleka | 2026-04-15 | 2 | 2026-04-17 | 2
Create statistics page | Tuleka | 2026-04-20 | 2 | 2026-04-22 | 2
Design and implement a categories screen. | Avuyile | 2026-04-22 | 1 | 2026-04-23 | 1
Add a gamification feature (rewards) | Avuyile | 2026-04-27 | 2 | 2026-04-29 | 2
Develop homescreen widget for quick expense logging. | Olilitha | 2026-04-29 | 2 | 2026-05-01 | 2
Begin notifications system (reminders, progress updates) | Olilitha | 2026-05-11 | 2 | 2026-05-13 | 2
Evaluation
Conduct usability testing (navigation, accessibility, responsiveness). | Tuleka | 2026-05-13 | 2 | 2026-05-15 | 2
Test widget integration across devices. | Olilitha | 2026-05-18 | 2 | 2026-05-20 | 2
Test shared wallet functionality. | Avuyile | 2026-05-20 | 2 | 2026-05-22 | 2
Identify and fix errors. | All members | 2026-05-22 | 3 | 2026-05-27 | 5
Final integration of all features. | Ondela | 2026-05-27 | 5 | 2026-06-03 | 7
Deploy prototype for evaluation. | Olilitha | 2026-06-05 | 2 | 2026-06-09 | 4
Finalisation
Compile documentation with screenshots of the final prototype. | All members | 2026-06-08 | 2 | 2026-06-10 | 2
Update documentation and read me file | Avuyile | 2026-06-12 | 2 | 2026-06-14 | 2
Submit BloomBudget app and Planning & Design report. | Olilitha | 2026-06-14 | 1 | 2026-06-15 | 1
Formulas:
End Date = WORKDAY([Start Date],[Days needed])